## Product Backlog
Product Name: | ELSA | [6 empty] | Complete Fields in Green!!!
Team ID: | Jam915
| Team Member Name | [5 empty] | Initials | Student ID
Required | Jesse McNary | [5 empty] | JAM | 1001942779
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 23 |  |  |  | Total | Total number of features (in column H)
1 | 18 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 12 | 6 |  |  | 2 | Total features left at the end of Sprint #2
3 | 10 | 2 |  |  | 3 | ...and so on
4 | 10 | 0
5 | 10 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
[5 empty] | Sprint to which Feature is Assigned |  |  | Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly | Validate the email address (lightly)
OPT | 2 | 1 |  | 3 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product | Validate that the cost is not negative
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
STORE | 5 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Provide a central collection of the above data | Create and manage information to run my store efficiently
WIN | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | Sales Staff | Add a GUI main window with menubar | Use it more easily | Recommend baselining Nim from Lecture 12
INSCU | 7 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Customers via a sequence of dialogs | Do everything within the GUI | Recommend JOptionDialog from Lecture 13
INSOP | 8 | 2 |  | 3 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Options via a sequence of dialogs | Do everything within the GUI
INSCO | 9 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Computers via a sequence of dialogs | Do everything within the GUI
DISP | 10 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | List data (customers, options, and computers separately) in the main window display | Access the data directly in the window | You’ll need a View menu for this, and perhaps a JLabel in the main window center section
TOOLB | 11 | 2 |  | 8 | 2 | Finished in Sprint 2 | Sales Staff | Add a simple toolbar to the main window | Use the app with pushbutton convenience | Part of the Nim baseline. Create your own icons or find some online.
ABOUT | 12 | 3 |  | 2 | 3 | Finished in Sprint 3 | Director | (If needed) Provide a simple text-only About dialog | Avolid a lawsuit | (If needed) Rewrite the text from Nim's implementation to comply with toolbar icon license obligations
ABOSK | 13 | 3 |  | 5 | 3 | Finished in Sprint 3 | Director | Provide About dialog with sketch as or around a bitmap logo for aesthetics and documenting licenses | Impress users | Recommend a subclass of JPanel from Lecture 15 with a simple diagram plus Jlabels in one or more JPanels with program information
SAVE | 14 | 3 |  | 13 | 3 |  | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save (via method) and reload (via constructor) each object from a provided stream
NEW | 15 | 3 |  | 1 | 3 |  | Manager | Create a new, empty store | Start new franchises | This is as easy as “new Store” with a name
SAVAS | 16 | 3 |  | 5 | 3 |  | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use JfileChooser
LOAD | 17 | 3 |  | 8 | 3 |  | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use JfileChooser
SPEC | 18 | 4 |  | 13 |  |  | Customer | Store and display type-specific data | Ensure I purchase the correct product | Use inheritance with polymorphism
INSOR | 19 | 4 |  | 5 |  |  | Sales Staff | Insert new Computers via a sequence of dialogs | Do everything within the GUI
DISP2 | 20 | 4 |  | 1 |  |  | Sales Staff | List ORDERS in the main window display | Access the order data | This is a minor change
DCUST | 21 | 4 |  | 8 |  |  | Sales Staff | Replace sequencial dialogs with custom dialogs | Enter data more quickly | More practice with custom dialogs
GEN | 22 | 4 |  | 8 | [5 empty] | Use a generic in some way (TBD)
UNIQ | 22 | 5 |  | 5 |  |  | Manager | Avoid duplicate data entry | Keep the database clean | Require a Set or Map with hashCode implementations
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
SCROL |  |  |  | 5 |  |  | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR |  |  |  | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR |  |  |  | 8 |  |  | Manager | Add a status bar to the main window | Better track status of messages | A stack of messages that can be reviewed would be worth more!
DTAIL |  |  |  | 21 |  |  | Customer | Provide a detail view of a product type info in the main window | Provide additional info about each product
PIX |  |  |  | 13 |  |  | Customer | {Prerequisite: DTAIL} Include a picture of the product in its detail view | Save a thousand words | The image can be a file. Store the filename in Option, and load from disk when required

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2023-03-07 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 2
Day 1 Left | 0 | 2
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | ABOUT | JAM | Create About Diolog for Photos | Completed Day 1
2
3 | ABOSK | JAM | Create turtle image using template in 1325-prof | Completed Day 1
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2023-02-28 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 20
Day 1 Left | 20 | 0
Day 2 Left | 10 | 10
Day 3 Left | 6 | 4
Day 4 Left | 2 | 4
Day 5 Left | 0 | 2
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN | JAM | Transfer files over from NIM | Completed Day 2
2 | WIN | JAM | Renamefiles and begin working on MainWin | Completed Day 2
3 | WIN | JAM | Get gui with Menubar setup | Completed Day 2
4 | WIN | JAM | Begin working on actionListeners | Completed Day 2
5
6 | INSCU | JAM | Begin constructing the onInsertCustomerClick() | Completed Day 2
7 | INSCU | JAM | Test onInsertCustomerClick() using gui only | Completed Day 2
8 | INSCU | JAM | Git add, commit, push | Completed Day 2
9 | INSOP | JAM | Begin constructing the onInsertOptionClick() | Completed Day 2
10 | INSOP | JAM | test onInsertOptionClick() using gui only | Completed Day 2
11 | INSOP | JAM | Git add, commit, push | Completed Day 2
12
13 | INSCO | JAM | Construct onInsertComputerClick() | Completed Day 3
14 | INSCO | JAM | test with gui only | Completed Day 3
15 | INSCO | JAM | Git add, commit, push | Completed Day 3
16
17 | DISP | JAM | Construct onViewClick() method | Completed Day 3
18 | DISP | JAM | test with gui only | Completed Day 4
19 | DISP | JAM | Git add, commit, push | Completed Day 4
20
21 | TOOLB | JAM | Construct each button for the Toolbar | Completed Day 4
22 | TOOLB | JAM | Find Photos for each button on the Toolbar | Completed Day 4
23 | TOOLB | JAM | Test with gui | Completed Day 5
24 | TOOLB | JAM | Git add, commit, push | Completed Day 5
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2023-02-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-02-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 24
Day 1 Left | 10 | 14
Day 2 Left | 0 | 10
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | CUST | JAM | Write Customer Class | Completed Day 1
2 | CUST | JAM | Copy build.xml into repo and test compiule customer | Completed Day 1
3 | CUST | JAM | Test TestCustromer regression test | Completed Day 1
4 | CUST | JAM | Add Customer.java and build.xml to Github | Completed Day 1
5
6 | OPT | JAM | Write Option Class | Completed Day 1
7 | OPT | JAM | Test TestOption regression test | Completed Day 1
8 | OPT | JAM | Add Option.java to Github | Completed Day 1
9
10 | DESKT | JAM | Write Computer Class | Completed Day 1
11 | DESKT | JAM | Add name, model and options fields | Completed Day 1
12 | DESKT | JAM | Create constructer | Completed Day 1
13 | DESKT | JAM | add addOptions, cost, toString, and equals methods | Completed Day 1
14 | DESKT | JAM | Add Computer.java to github | Completed Day 1
15
16 | ORDER | JAM | Write Order class | Completed Day 1
17 | ORDER | JAM | Add nextOrderNumber, orderNumber, customer and computers fields | Completed Day 1
18 | ORDER | JAM | Write constructor | Completed Day 2
19 | ORDER | JAM | Write addComputer, toString, and equals methods | Completed Day 2
20 | ORDER | JAM | Test TestOrder regression test | Completed Day 2
21 | ORDER | JAM | Add Order to Github | Completed Day 2
22
23 | STORE | JAM | Create Object Customer | Completed Day 2
24 | STORE | JAM | Create Object Option | Completed Day 2
25 | STORE | JAM | Create Object Computer | Completed Day 2
26 | STORE | JAM | Create Object Order | Completed Day 2
27 | STORE | JAM | Confirm all 4 objects are created without error | Completed Day 2
28 | STORE | JAM | Add, commit, push Sprint 1 | Completed Day 2
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2023-04-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2023-04-18 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-25
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 6 | BONUS | Complete Fields in Green!!!
Start on | 2023-04-25 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-05-02
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
NOTE: This sprint is entirely OPTIONAL – no points will be lost if you ignore it
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84